## Slide 1: TGaz Next Generation Positioning March Electronic Meeting Closing Report
Date: 2021-03-11
Authors:

## Slide 2: Abstract
This document is the TGaz Next Generation Positioning closing report for the IEEE 802.11 interim electronic meeting, March 2021.

## Slide 3: TG Status And Work Completed
Work completed:
  Reviewed/approved 73 comments.
  Conducted comment assignment to additional 78 comments.
  Reviewed progress towards July LB recirculation.
  Initiated MDR process and received most of the findings (editors).

## Slide 4: Timeline – updated past March meeting
2021
2020
2019
2017
2018
2022
2023
.11az requirement freeze
5-2017
11az SFD
Amendment text
.11az Draft 2.0 11-2019
Recirculation
D1.0
Jan. 19
.11az D0.1 Mar. 18
5/17-3/21
July 18
Inter.
comment
collection
SFD
Final
Initial
WG ballot
CC28
LB240 CR
Initial WG ballot LB240 Pass
SFD Freeze
LB249
LB240 completion/
recirc. init
LB249 completion/
2nd recirculation
.11az Draft 3.0 01-2021
Recirculation
.11az Draft 4.0 07-2021
Recirculation
.11az MDR and SA ballots
07-2021
Publication
LB253
2nd SA
MDR
1st SA
Next
LB
Clean
No changes made, in preparation to SA ballot
1st SA comp.
2nd SA comp.

## Slide 5: Goal Towards May Meeting and Beyond
Continue LB253 comment resolution.
Generate P802.11az D3.1 adopting resolutions from March meeting.
Response to MDR findings (Editors).

## Slide 6: Teleconference Schedule till the May meeting
March 17*, 31 13:00 – 15:00 ET
March 25+ 10:00 – 12:00 ET
April 7,14,21 13:00 – 15:00 ET
April 29 + 10:00 – 12:00 ET
May 5, 26 13:00 – 15:00 ET
*Previously announced.
**WG May meeting is running May 10th – 18th , refer to WG agenda doc.
+ Plenary (motion) meeting.